## Estimate Template
Decomposition Item | Comments | Dependencies | Priority | Optimistic (man/days) | Pessimistic (man/days) | Mosk Likely (man/days) | Expected (man/days) | Unit Testing (man/days) | Code Review (man/days) | Defect Fixing (man/days) | Final Expected (man/days)
Environment Setup | Initial configurations for tools and services | - | High | 2 | 3 | 4 | 3 | 0.75 | 0.3 | 0.6 | 4.65
Design Platform | UI/UX designs | Environment Setup | High | 3 | 6 | 8 | 5.6667 | 1.4167 | 0.56667 | 1.1333 | 8.7833
AI Integration | Integrating trained AI models | Design Platform | Medium | 4 | 7 | 7 | 6 | 1.5 | 0.6 | 1.2 | 9.3
Game Development | Development of core game mechanics, including player interaction and AI | AI Integration | Medium | 5 | 6 | 6 | 5.6667 | 1.4167 | 0.56667 | 1.1333 | 8.7833
Leaderboard Development | Building a player ranking system with database integration | Game Development | Medium | 6 | 5 | 5 | 5.3333 | 1.3333 | 0.53333 | 1.0667 | 8.2667
Testing and Deployment | Performing final integration testing before deploying in a cloud environment | Leaderboard Development | Medium | 7 | 3 | 3 | 4.3333 | 1.0833 | 0.43333 | 0.86667 | 6.7167
Documentation Creation | Documentation depends on the test results. | Testing and Deployment | High | 8 | 8 | 5 | 7 | 1.75 | 3.5 | 1.4 | 13.65
User Registration | Implementing user onboarding | Documentation Creation, AI Integration | High | 9 | 7 | 3 | 6.3333 | 1.5833 | 0.63333 | 1.2667 | 9.8167
Security Implementation | Ensuring security compliance | User Registration | Medium | 0 | 5 | 3 | 2.6667 | 0.66667 | 0.26667 | 0.53333 | 4.1333
Final Adjustments | Final touches and delivery | Security Implementation | Low | 4 | 4 | 3 | 3.6667 | 0.91667 | 0.36667 | 0.73333 | 5.6833
Subtotal |  |  |  | 48 | 51 | 47 | 49.6667 | 12.4167 | 7.7667 | 9.9333 | 79.7833

## How to Use This Template
Activity Type | % from efforts on implementation
Unit Testing | 25%
Code Review | 10%
Bug Fixing | 20%
Activity Type | % from dev efforts
Manual QC | 50%