## Лист2
|  |  |  | Labor |  | Materials | [7 empty] | Risk of contingecy |  | Managment Reserve | ACTUAL | ACTUAL + 12%
|  |  | Planned Hours | Actual Hours | $/HR | UNITS | $/UNITS | Travel | Equipment | Labor Cost | Materials Cost | Fixed Costs | BUDGETED | 7% | Misc. | 5%
| Project Activities | Assigned To: | [10 empty] | 169220 |  |  |  | 169720 | 202074.71
1 | Environment Setup | Team A | 80 | 78 | 50 | 10 | 100 | 500 | 2000 | 3900 | 1000 | 500 | 12900 | 1463 | 50 | 1088.15 | 12950 | 15451.15
2 | Design Platform | Team B | 100 | 102 | 45 | 15 | 80 | 600 | 1500 | 4590 | 1200 | 800 | 14390 | 1621.2 | 50 | 1205.06 | 14440 | 17216.26
3 | AI Integration | Team C | 120 | 118 | 60 | 5 | 150 | 400 | 1800 | 7080 | 750 | 400 | 18380 | 2027.2 | 100 | 1521.86 | 18480 | 21929.06
4 | Game Development | Team D | 200 | 195 | 55 | 20 | 120 | 700 | 2500 | 10725 | 2400 | 700 | 30425 | 3329.9 | 50 | 2503.995 | 30475 | 36258.895
5 | Leaderboard Development | Team E | 150 | 148 | 50 | 10 | 100 | 650 | 2200 | 7400 | 1000 | 600 | 20350 | 2261 | 50 | 1690.55 | 20400 | 24301.55
6 | Testing and Deployment | Team F | 180 | 182 | 60 | 25 | 90 | 500 | 2000 | 10920 | 2250 | 550 | 29270 | 3190.6 |  | 2409.03 | 29270 | 34869.63
7 | Documentation Creation | Team G | 90 | 88 | 40 | 5 | 50 | 300 | 1200 | 3520 | 250 | 300 | 9420 | 1052.8 | 50 | 787.14 | 9470 | 11259.94
8 | User Registration | Team H | 75 | 74 | 45 | 8 | 70 | 400 | 1500 | 3330 | 560 | 350 | 10075 | 1139.95 | 50 | 847.7475 | 10125 | 12062.6975
9 | Security Implementation | Team I | 110 | 112 | 50 | 10 | 85 | 450 | 1800 | 5600 | 850 | 450 | 15500 | 1731.45 | 50 | 1296.5725 | 15550 | 18528.0225
10 | Final Adjustments | Team J | 50 | 52 | 55 | 5 | 110 | 300 | 1000 | 2860 | 550 | 500 | 8510 | 968.1 | 50 | 719.405 | 8560 | 10197.505
| SUBTOTAL |  |  |  | 59925 |  | 10810 | [5 empty] | 169220 |  | 350 |  | 169720 | 202074.71
Task: Enter the name of the task being worked on.
Assigned To: Who is responsible for the task
Planned HR: Enter the number of hours you expect the task to take.
Actual HR: Enter the number of billable hours the work actuallty took.
Labor $/HR: Enter how much money per hour that labor cost you.
Materials UNITS: Enter how many units of material you needed to complete the task.
Materials $/UNITS: Enter how much money each unit cost.
Travel: Enter the total travel expenses.
EQUP/SPACE: Enter how much your equipment or office space costs.
FIXED: Enter any costs that are fixed and unchanging.
MISC: Enter any other known costs.
BUDGET: Enter your budget for the task.
ACTUAL: This field will be automatically calculated based on the other costs entered in the row.
SUBTOTAL: This row sums all the rows above it to give you a subtotal for the project.